## Sheet1
TOURNAMENT CHECK LIST FOR (NAME OF YOUR TOURNAMENT)
2023-04-02 | <- Date of Your Tournament | (Put the date in A3 and all the due dates will populate automatically) | TTV Office | Tournaments Committee | Host Affiliate
| June Previous Year | Start of next years' calendar preparation | ü | ü | ü
| October Previous Year | Entry forms to be set up on RevSport portals | ü | ü | ü
|  | Determine events and timing | ü | ü | ü
|  | Draft entry form | ü | ü | ü
|  | Proof read entry form | ü | ü | ü
|  | Approve entry form | ü | ü | ü
| November Previous Year | Next years' TTV calendar published | ü
DUE DATES:
2023-01-14 | WEEK - 11 | Identify who will be running the tournament on Zermelo |  | ü | ü
|  | If noone from the Affiliate can use Zermelo, please contact TTV | ü |  | ü
2023-01-21 | WEEK -10 | Tournament Poster with QR code and dates to be finalised | ü |  | ü
|  | Posters to be emailed to all Affiliates for their notice boards | ü
2023-01-31 | WEEK -9 | Entries Open on RevSport Portal | Automated |  | Automated
|  | Social Media Posts | ü |  | ü
|  | Ask TTVUL to send out request for Officials | ü
| WEEK -6, -7, -8 | Arrange tournament assistants |  |  | ü
|  | Book accommodation where required for Officials | ü
|  | Book accommodation where required for Tournament Staff/Volunteers |  |  | ü
|  | Distribute posters to affiliates | ü
|  | Social Media Posts | ü |  | ü
|  | Monitor entries per event. |  | ü | ü
|  | Reconcile on RevSport any fees paid via Bank Deposit |  |  | ü
|  | Send reminder invoices for unpaid fees |  |  | ü
|  | Start Zermelo set up - event names |  |  | ü
| WEEK -3, -4, -5 | Entering names into Zermelo as entries come in |  | ü | ü
|  | Social Media Posts | ü |  | ü
|  | Monitor entries per event. |  | ü | ü
|  | Reconcile on RevSport any fees paid via Bank Deposit |  |  | ü
|  | Send reminder invoices for unpaid fees |  |  | ü
2023-03-18 | DAY -15 | Entries Closed | Automated |  | Automated
2023-03-19 | DAY -14 | Send TTVUL the final number of entries/budget for the Officials | ü
|  | Make sure there are enough balls available - order more if needed |  |  | ü
|  | Check all scoreboards and clip boards are in working order - order more if needed |  |  | ü
2023-03-20 | DAY -13 | Finalise names in Zermelo |  | ü | ü
|  | Send Player List from Zermelo to the Selectors |  | ü | ü
|  | Match up individuals wanting doubles partners |  | ü | ü
2023-03-21 | DAY -12 | Finalise trophies & inform supplier |  |  | ü
|  | Write to special trophy presenters |  |  | ü
2023-03-25 | DAY -8 | Seedings returned by Selectors | ü
|  | Make any changes to RC points as required by the Selectors in Zermelo |  | ü | ü
|  | Produce draft draws & rectify problems in them |  | ü | ü
|  | Confirm tournament assistants |  |  | ü
|  | Confirm officials | ü |  | ü
2023-03-28 | DAY -5 | Send the draft draw to the Referee for approval |  | ü | ü
|  | Confirm bookings for microphone, tables, chairs, power cords |  |  | ü
|  | Accurately calculate tables required |  | ü | ü
|  | Determine potential problem players (multiple seedings & max events) |  | ü | ü
|  | Establish detailed event timing plan & first matches to be played |  | ü | ü
|  | Prize Money calculating | ü |  | ü
|  | FINAL NOTICE to all players who have no paid - NO PAY = NO PLAY |  |  | ü
2023-03-30 | DAY -3 | Publish approved draft draw on website | ü
|  | Receive trophies |  |  | ü
|  | Arrange catering for volunteers |  |  | ü
|  | Pre tournament interview with TTV MMO for "Event Preview" article | ü |  | ü
2023-04-01 | DAY -1 | Print final draws and back-up match cards |  |  | ü
|  | Post draws up on wall |  |  | ü
|  | Ready computer/s, printers, set up office & trophies |  |  | ü
|  | Ready balls, camera, pencils, sponsor's materials |  |  | ü
|  | Ready scoreboards and clip boards |  |  | ü
|  | Finalise trophy presenters and confirm with them |  |  | ü
2023-04-02 | TOURNAMENT DAY | Open office, set up tables & equipment, set up microphone, set up sponsor's material |  |  | ü
|  | Tournament underway |  | ü | ü
|  | Trophies Presentations |  |  | ü
|  | Follow up on EFT details from players who have won but hadn't supplied when entering |  |  | ü
| End of the Day | Upload results to Ratings Central |  |  | ü
|  | Produce Finalist report for Prize Money payment |  |  | ü
|  | Print as PDF all results and publish to RevSport (& sent to TTV) | ü |  | ü
2023-04-04 | DAY +2 | Pay Prize Money via EFT to all recipients |  |  | ü
|  | Pay Officials via EFT | ü
2023-04-09 | WEEK +1 | TTVUL Report to TTV |  |  | ü
|  | Produce event reports |  |  | ü
|  | Post tournament committee meeting |  |  | ü
|  | Write review & evaluation report |  |  | ü
|  | Write and thank assistants |  |  | ü
|  | Post tournament interview with TTV MMO for "Event Recap" article | ü |  | ü